## Sheet1
Wearable Workshop Task List- Final 3 weeks
Due Date | Item | Category | Assignment | Comments | Status | More Comments
2014-11-22 | PR campaign launched | PR | All Volunteers | See details under PR page | 2
2014-11-22 | Update blog | PR |  | Update info for wearable workshop | 2
2014-11-23 | Follow up with Guest Speakers | Day of Logistics |  | See notes | 1
2014-11-23 | Curriculum- Wearable Circuit | Curriculum |  |  | 0
2014-11-23 | Publicize Guest Speaker | PR |  |  | 2
2014-11-24 | Volunteer Update | Volunteers |  | Additional assignments, role descriptions (Add reflection faciliitator), lunch survey | 2
2014-11-24 | Misc. Supplies Ordered | Preparation |  |  | 2
2014-11-24 | Email Joyce Michaels regarding TOIL Assist. |  |  |  | 2
2014-11-28 | Finish volunteer packet for wearable circuit | Volunteers |  | Or sooner | 0 | Touched base :)
2014-11-28 | Send materials to Dave Scott | TOIL Tour |  |  | 2
2014-11-28 | Finish volunteer packet for Solidworks | Volunteers |  |  | 0 | Saturday- download autocad on outreach laptops and
2014-12-01 | Sandwich reminder for volunteers, and prep session |  |  |  | 1 | Send out additional email over weekend/sort through day of assignments/call people
2014-12-01 | Email volunteers final instruction packets | Volunteers |  |  | 0
2014-12-01 | PR campaign ends | PR |  |  | 2
2014-12-04 | Girl sign ups done | Participants |  |  | 2 | Follow up with payments
2014-12-01 | Laptops collected |  |  | Where they are/software | 0 | conops for outreach laptops, email girls download | Tonight
2014-12-03 | Payment follow up for girls |  |  |  | 2
2014-12-01 | Fab Program follow up | Participants |  |  | 2
2014-12-03 | Fill out conops |  |  |  | 0 | Call tomorrow
2014-12-05 | Outdoor signs |  |  | Survey printed, check in booth print outs- additional forms | 1
2014-12-05 | Solder team |  |  |  |  | Tonight
2014-12-03 | Send security list of people |  |  |  | 2
2014-12-05 | Practice Intro to Wearables | Curriculum |  |  | 0
2014-12-05 | Map of the day | Day of Logistics |  |  | 2
2014-12-05 | AV Request | Day of Logistics |  |  | 2
2014-12-05 | Security Memo follow up | Day of Logistics |  |  | 2
2014-12-05 | Food ordered | Day of Logistics |  |  | 2
2014-12-05 | Finish laser cut bags
2014-12-05 | Define Path to TOIL Lab | Day of Logistics |  | Need to Contact Security | 2
2014-12-08 | Goodie bag items collected | Preparation |  |  | 2
2014-12-08 | 3d Bracelets printed and dropped off at preparation session | Preparation |  | Meeting with Dave Scott 11/24 | 1 | Tonight
2014-12-08 | Prep Day 1 | Preparation |  | Wearables (Cut LEDs, velostat, solder LEDs), Stuff goodie bags (items from outreach, print out flyer, bracelets), Set up Laptops | 2
2014-12-08 | Prep Wearables Volunteers | Volunteers |  |  | 0
2014-12-08 | Follow up with Photographer | Day of Logistics |  | Discuss schedule of day | 2
2014-12-09 | TOIL Dry Run | TOIL Tour |  |  | 0 | Tonight- materials
2014-12-10 | Print out survey |  |  |  | 2
2014-12-10 | Raffle | Day of Logistics |  | Collect items (Red bracelets, Sweatshirts, Lasercut purses, 1 Arduino), print out names, put into bag | 2 | Make a list of items
2014-12-10 | Make a spread sheet of laptops- who has what and what software is on them
Email head of secretary of educatino
Make extra copies of software/assign someone to be the IT help desk
Demonstration- shoe, done kit
Extra soldering and kits
Install arduino software on all computers/check kits
Stuff the rest of the goodie bags..solidworks stuff and printouts
Get tshirts ready for volunteers
Signs and mouse…
2014-12-10 | Check all the kits to see if they work- make a spread sheet
2014-12-12 | Monitor Set up on Friday afternoon |  |  |  | 1
2014-12-11 | Prep Day 2 | Volunteers | All Volunteers | Prep facilitators (run through projects), dry run talks, finish soldering LEDs | 0
2014-12-12 | Prep Day 3 | Volunteers | All Volunteers | Prep facilitators (run through projects), dry run talks | 0
2014-12-12 | Pick up sandwiches | Day of Logistics |  |  | 2
2014-12-12 | Buy water and drop off at Cafeteria next morning | Day of Logistics |  |  | 2
2014-12-13 | Buy donuts and coffee for volunteers | Day of Logistics |  |  | 0
2014-12-15 | Volunteer Party | Post Event |  | TBD | 0
2014-12-15 | Reimburse MITLL | Post Event |  |  | 0
2014-12-15 | Survey to Participants | Post Event |  |  | 0
2014-12-20 | Thank You Notes | Post Event |  |  | 0
2014-12-20 | Send Pictures and Summary to Interested Parties | Post Event |  | MITLL Outreach, Made With Code, Make Magazine | 0
Survey to volunteers
write report with budget and girls' responses
photos
follow up thank you email to volunteers and gils- facilities, av equip, security
katy's doggle
sort all of the laptops
follow up with solidworks, barbra hughey
sort through random items/kits
final volunteer list and girls list

## Sheet2
PR | 0
Participants | 1
Curriculum | 2 | day 1 | day 2 | day 3
Preparation |  | Cut LEDs, solder, wires, velostat | wearable circuit prep | wearable circuit prep
Volunteers
TOIL Tour
Day of Logistics
Misc
Misc